## Sheet1
| Requirement | Priority | Percent of complition | Phase | To be completed by | Comment
1 | Suggested to add a drop-down list, which will suggest a list of previously created and open tickets, that a new one might be connected to. To translate to L1 Support employees the importance of updating existing cases and enforce a practice of setting appropriate status to the tickets. | Medium | 100% | Phase 1 - Completed | 2019-06-16
2 | Prioritization questions to be part of the ticket, where the L1 staff answer and prioritize accordingly. Incident priority to follow our PPG prioritization matrix. | High | 100% | Phase 1 - Completed | 2019-06-16
3 | L2 assignment to go in to a work queue where L2 staff can pick up these tickets and work on them. The work queue should have the prioritised tickets appearing at the top. | High | 100% | Phase 1 - Completed | 2019-06-16
4 | Each ticket must have a note from the L2 team if it’s been assigned to the L3/infrastructure teams. If Jira ticket is created, the ticket must have a comment with this update, in order to streamline the status of the issue between L1-L2-L3. | High | 100% | Phase 1 - Completed | 2019-06-16
5 | Each ticket shall have a ticket resolution box and root cause with description. | High | 50% | Phase 2 | 2019-06-25
6 | Communication to customer on resolution of the ticket (L1 to send the Incident Report). | High | 85% | Phase 2 | 2019-06-25 | Incident report to be revised: decide what shall be shared with the customer Process to be agreed
7 | SLA report from the system (Ticket Created Date -> Ticket Resolved Date -> Ticket Closed Date) | Medium | 0% | Phase 2 | 2019-07-04
8 | OLA report from the system - Ticket in L1 total duration (within OLA / exceeding OLA), Ticket in L2 total duration (within OLA / exceeding OLA), Ticket in ‘Assigned to L3 / Infrastructure status’ total duration (within OLA / exceeding OLA). | Medium | 0% | Phase 2 | 2019-07-04
9 | L3 assignment integrated with JIRA and the system to fetch the closed ticket in JIRA and notify L2. | High | 100% | Phase 1 - Completed | 2019-06-16
10 | Automated OLA escalations based on our SLA / OLA Matrix. | High | 100% | Phase 1 - Completed | 2019-06-16
11 | Email templates for escallations | High | 50% | Phase 2 | 2019-06-25
12 | Email templates for customers | High | 50% | Phase 2 | 2019-06-25 | L1 can send email manually (Open, RFI, Resolved)
13 | Email templates internal | High | 50% | Phase 2 | 2019-06-25
14 | Jira assign to application product managers (they are part of L3 product group) | High | 100% | Phase 1 - Completed | 2019-06-16 | Will be assigned to L3 product group including Procuct Manager
15 | Ticket status to be cleared (+ Status: Faiting for Info) | High | 100% | Phase 1 - Completed | 2019-06-16
16 | Ticket assignment dropdown to be cleared (L2, L3, infra, business, QA) | High | 100% | Phase 1 - Completed | 2019-06-16
17 | 4 fields for priority and severity (2 for client and 2 internal) | High | 100% | Phase 1 - Completed | 2019-06-16
18 | Each field while ticket creation shall have a hint with "what shall be filled here" for L1 team | Medium | 0% | Phase 2 | 2019-07-04
19 | Infrastructure internal system integration with ticketing system | Medium | 0% | Phase 2 | 2019-07-04
20 | L2 staff automatic assignment from the L2 work queue. | Low | 0% | TBD | TBD
21 | To add a drop down with most common answers to the fild: Actions Taken for L1 with option:other and free text | Medium | 0% | Phase 2 | 2019-07-04
22 | To send all ticket notifications to the email group: ppg@iqvia . Com | Medium | 100% | Phase 1 - Completed | 2019-06-16 | new (13 June)
23 | Smart box in for Subject with dropdown | Medium | 0 | Phase 2 | 2019-07-04
24 | Role bases Functionality: Admin Role | Medium | 100% | Phase 1 - Completed | 2019-06-16
25 | Role based functionality: L1 Role | Medium | 100% | Phase 1 - Completed | 2019-06-16
26 | Role based functionality: L2 Role | Medium | 100% | Phase 1 - Completed | 2019-06-16
27 | After 5 days of ticket closure automatic ticket update to closed status. CLient acknowledgment of ticket closure | High | 50% | Phase 2 | 2019-06-25
28 | Add option to delete attachment in the system | Low | 0% | TBD | TBD
30 | Create more themes for the site | Low | 0% | TBD | TBD
31 | Role based functionality: L3 Role | Medium | 100% | Phase 1 - Completed | 2019-06-16
32 | Role based functionality: Business Team Role | Medium | 0% | Phase 2 | 2019-06-25
33 | Role based functionality: Management Role | Medium | 0% | Phase 2 | 2019-06-25
34 | Phase 4 : CISCO | Low | 0% | TBD | TBD
36 | Client Engagement portal | Low | 0% | TBD | TBD
37 | Chat Services | Low | 0% | TBD | TBD
38 | Email Automation / Phone Automation | Low | 0% | TBD | TBD
39 | API expose to create ticket | Low | 0% | TBD | TBD
41 | KB to be merged with group of title | Low | 0% | TBD | TBD
42 | Enhance KB view (add roles of the persons L1,L2,L3) | Low | 0% | TBD | TBD
44 | Integrate with Sales Force | Low | 0% | TBD | TBD
45 | SMS/Whatsapp notification | Low | 0% | TBD | TBD
46 | Call to be sent from the system | Low | 0% | TBD | TBD
49 | Caller Issues Report | Low | 0% | TBD | TBD
50 | Caller Issues Status Report | Low | 0% | TBD | TBD
52 | Integration with Sharepoint | Low | 0% | TBD | TBD
54 | Postmortam Report | Low | 0% | TBD | TBD
55 | KPI landing page | Low | 0% | TBD | TBD
56 | Change font to Tahoma/Callibre | Low | 100% | Phase 1 - Completed | 2019-06-16
57 | Grouping of ticket report | Low | 0% | TBD | TBD
59 | Check if we have KB while creating Ticket, ticket view shall have KB | Medium | 0% | Phase 2 | 2019-06-25
61 | TWC: ticket without caller | Low | 0% | TBD | TBD